## Week
TabUltra | [20 empty] | Project Schedule
|  | Start Week | 2022-02-05
Week | 1 | 1 | 2 | 2 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11
Starting | 2022-02-05 | 2022-02-12 | 2022-02-19 | 2022-02-26 | Feb | Mar | Mar | Mar | Mar | Mar | Mar | Mar | April | April | April | April | April | April | April | April | Notes
| 2022-02-05 | 1900-01-09 | 1900-01-14 | 1900-01-18 | 1900-01-23 | 1899-12-31 | 1900-01-04 | 1900-01-09 | 1900-01-14 | 1900-01-18 | 1900-01-23 | 1900-01-28 | 1900-01-01 | 1900-01-06 | 1900-01-12 | 1900-01-15 | 1900-01-20 | 1900-01-23 | 1900-01-24 | 1900-01-29
Phase | Rolls Assigned *
One | Informal Req. Doc.
JavaScript/HTML research
UI/Web mockup
Phase |  |  |  |  | Finalized Req. Doc
Two |  |  |  | Window/UI Implementation
Reg/Sel. Tabs Func
Group/Save Tabs Func
Group Manage. Func
Landing Page Implementation
Group Metadata
Phase | [11 empty] | Heavy Limit Testing
Three | [12 empty] | Finalized Landing Page
Ext. Upload/Fixes
Final UI Layout
Final Additions

## Month
Project Title | [24 empty] | Project Schedule
© 2014-2019 Vertex42 LLC
|  | Start Date | 2019-06-03 | [22 empty] | Project Schedule Template
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  | Edit the Start date in cell E3
| 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | Notes
| 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01
Phase | [25 empty] | RELATED TEMPLATES
One | [25 empty] | ► Gantt Chart Template
► Project Management Templates
► Business Templates
Phase
Two
Phase
Three

## Sample
Project Title | [20 empty] | Project Schedule
© 2014-2019 Vertex42 LLC
|  | Start Week | 2014-01-05 | [18 empty] | Project Schedule Template
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  | Edit the Start date in cell E3
Starting | 2014-01-05 | 2014-01-12 | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02 | 2014-03-09 | 2014-03-16 | 2014-03-23 | 2014-03-30 | 2014-04-06 | 2014-04-13 | 2014-04-20 | 2014-04-27 | 2014-05-04 | 2014-05-11 | 2014-05-18 | Notes
| 2014-01-05 | 2014-01-12 | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02 | 2014-03-09 | 2014-03-16 | 2014-03-23 | 2014-03-30 | 2014-04-06 | 2014-04-13 | 2014-04-20 | 2014-04-27 | 2014-05-04 | 2014-05-11 | 2014-05-18
Phase | 2014-01-05: Quality Assurance Plan; 2014-05-18: P R O J E C T E N D |  | RELATED TEMPLATES
One | 2014-01-12: Project Plan |  | ► Gantt Chart Template
| 2014-01-19: Plan Review |  | ► Project Management Templates
Phase | 2014-01-26: Draft Requrements |  | ► Business Templates
Two | 2014-01-26: Capacity Planning
Project Test Plan
Acceptance Test Plan
Final Requirements Specifications
Phase Review and Approval
Phase | 2014-02-16: Milestone: additional funds; 2014-02-23: Draft Design Specifications
Three | 2014-02-23: Configuration Management Plan
Architectue Design Plan
Define Interface Requirements
Shared Component Design
Integration Test Plan
Define Project Guidelines
Final Design Specifications
Phase Review and Approval

## Help
HELP
http://www.vertex42.com/ExcelTemplates/project-schedule-template.html |  | © 2014-2019 Vertex42 LLC
About This Template
This project schedule can be used to create a basic timeline for your project. It gives you a lot of flexibility, but formatting is completely manual.
Try the Vertex42 Gantt Chart Template if you want to something more automated for creating and managing your project schedule.
► Gantt Chart Template
How to use this Template
1) | Enter your project start date in cell E3. This will automatically update the dates in rows 6 and 7.
2) | Add tasks: Choose what phase (row) and week (column) the task will start and enter the task title into that cell. Then fill in the background color of the cells to indicate how long the task will take to complete.
If you would like to show the completion status of a task, you can fill the background with a darker or different color (see the Sample worksheet for an example).
3) | Add a milestone: If you'd like to show a milestone, you can create a vertical "line" in the schedule by changing the cell borders and the background fill (see the Sample worksheet).
Note: In the sample worksheet, the Project End milestone was created by merging cells, turning on Wrap Text, and pressing Alt+Enter after each letter to force each letter onto a new line.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.
Related Templates
► Gantt Chart Template
► Project Management Templates
► Business Templates

## ©
Project Schedule Template
By Vertex42.com
http://www.vertex42.com/ExcelTemplates/project-schedule-template.html
© 2014-2019 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it.